## Sheet1
To Do List
Task | Status | Priority | Due Date | Assignee | Notes
1.1. Purpose of the System | Completed | High | 2016-07-16 | Emine Yıldız | System Design Document
1.2. Design Goals | Completed | High | 2016-07-16 | Emine Yıldız | System Design Document
1.3. Definitions, Acronyms, and Abbreviations | Completed | High | 2016-07-16 | Emine Yıldız | System Design Document
1.4. References | Completed | High | 2016-07-16 | Emine Yıldız | System Design Document
2. Current Software Architecture | Completed | High | 2016-07-16 | Aslı Tuba Metin | System Design Document
3. Proposed Software Architecture | Completed | High | 2016-07-16 | Selen Kozanoğlu | System Design Document
3.2. System Decomposition | Completed | High | 2016-07-16 | Arda Yazkan | System Design Document
3.3. Hardware Software Mapping | Completed | High | 2016-07-16 | Arda Yazkan | System Design Document
3.4. Persistent Data Management | Completed | High | 2016-07-16 | Aslı Tuba Metin | System Design Document
3.5. Access Control and Security | Completed | High | 2016-07-16 | Selen Kozanoğlu | System Design Document
3.6. Global Software Control | Completed | High | 2016-07-16 | Selen Kozanoğlu | System Design Document
3.7. Boundary Conditions | Completed | High | 2016-07-16 | Selen Kozanoğlu | System Design Document
4. Subsystem Services | Completed | High | 2016-07-16 | Emine Yıldız | System Design Document
1.1 Purpose of the System | Completed | High | 2016-06-26 | Aslı Tuba Metin | Requirement Analysis Document
1.2 Scope of the System | Completed | High | 2016-06-26 | Aslı Tuba Metin | Requirement Analysis Document
1.3 Objectives and Success Criteria of the Project 3 | Completed | High | 2016-06-26 | Aslı Tuba Metin | Requirement Analysis Document
1.4 Definitions, Acronyms and Abbreviations 3 | Completed | High | 2016-06-26 | Aslı Tuba Metin | Requirement Analysis Document
1.5 Overwiew | Completed | High | 2016-06-26 | Aslı Tuba Metin | Requirement Analysis Document
2.Current System | Completed | High | 2016-06-26 | Aslı Tuba Metin | Requirement Analysis Document
3. Proposed System | Completed | High | 2016-06-26 | Selen Kozanoğlu | Requirement Analysis Document
3.1. Overview | Completed | High | 2016-06-26 | Selen Kozanoğlu | Requirement Analysis Document
3.2. Functional Requirements | Completed | High | 2016-06-26 | Emine Yıldız | Requirement Analysis Document
3.3. Nonfunctional Requirements | Completed | High | 2016-06-26 | Emine Yıldız | Requirement Analysis Document
3.4.1. Scenarios | Completed | High | 2016-06-26 | Selen Kozanoğlu | Requirement Analysis Document
Object Model | Completed | High | 2016-06-26 | Arda Yazkan | Requirement Analysis Document
Dynamic Model | Completed | High | 2016-06-26 | Arda Yazkan | Requirement Analysis Document
4.Glossary | Completed | High | 2016-06-26 | Arda Yazkan | Requirement Analysis Document
Database Management | In Progress | High | 2016-07-20 | Aslı Tuba Metin | Coding Analysis and System
User Interface SubSystem | In Progress | High | 2016-07-21 | Arda Yazkan | Coding Analysis and System
Admin SubSystem |  | High | 2016-07-22 | Arda Yazkan | Coding Analysis and System
Restaurant SubSystem |  | High | 2016-07-23 | Emine Yıldız | Coding Analysis and System
Form SubSystem |  | High | 2016-07-24 | Selen Kozanoglu | Coding Analysis and System
Reservation SubSystem |  | High | 2016-07-25 | Aslı Tuba Metin | Coding Analysis and System
Main SubSystem |  | High | 2016-07-26 | Emine Yıldız | Coding Analysis and System
Perfect Search Method-BETA TEST |  | High | 2016-07-27 | Arda Yazkan,Aslı Tuba Metin | Coding Analysis and System
Complete to feedback from client |  | High | 2016-07-28 | Emine Yıldız,Selen Kozanoğlu | Coding Analysis and System
Complete to feedback from client |  | High | 2016-07-29 | Emine Yıldız,Selen Kozanoğlu | Coding Analysis and System
Complete to feedback from client |  | High | 2016-07-30 | Emine Yıldız,Selen Kozanoğlu | Coding Analysis and System
Complete to feedback from client |  | High | 2016-07-31 | Arda Yazkan,Aslı Tuba Metin | Coding Analysis and System
System full test |  | High | 2016-08-01 | All Members of Group | Coding Analysis and System
System full test |  | High | 2016-08-02 | All Members of Group | Coding Analysis and System
Odd final report |  | High | 2016-08-03 | All Members of Group | This Part will be divided for all members